## Manish
Date | Task | Time (Hours) | Remaks | Completion Time | Attendence
2024-07-30 | Brainstorming | 1 | Decided the Project Niche and Roles of Members | 11:30 | 9:00
2024-07-30 | Server Setup | 0.25 | Basic Setup DOne For access (Host Files Setup)
2024-07-30 | Project Plan | 2 | Database MySQL, Backend Laravel
2024-07-31 | Morning Group Meeting | 1 | Reviewd and Discussed the Work Done So Far | 10:00 | 9:00
2024-07-31 | Helped Database Team to Setup Database | 0.5 | Made a plan for Website Database | 22:30
2024-07-31 | Discussed UI Requirements with Design Team | 0.5 | Discusssed Required Changes As per instructions | 11:00
2024-07-31 | Proposal Creation | 4 | Project Overview, Target Audience, Personas etc. | 17:30
2024-08-01 | Morning Group Meeting | 0.5 | Reviewd the database designed and set daily goal | 9:30 | 9:00
2024-08-01 | Proposal | 1 | Proposal Setup and Arranged the content from team members | 11:30
2024-08-01 | Created Controllers, Models | 1 | Setup all the controllers and models required | 13:30
2024-08-01 | Started doing work on Front end coding
2024-08-02 | Morning Group Meeting | 0.5 | Previous day work discussion and set daily goals | 9:30 | 9:00
2024-08-02 | Started Working on front end | 2 | Product List Page Created, Routes updated | 11:30
2024-08-02 | Shopping Cart, Billing Page Created | 2 | CSS, HTML, JS for Shoppign Cart and Billing | 13:30
2024-08-02 | Thank you page, User Profile Page Created | 2 | Updated user login page structure and styling | 15:30
2024-08-06 | Morning Group Meeting | 1 | Discusses previous work and Assigned Tasks for Making Dynamic Pages | 10:00 | 9:00
2024-08-06 | Product List Page | 2 | Made the page dynmaic (Search, Category Filter, Links to details view, CSS) | 12:30
2024-08-06 | Contact Page | 1 | Created Contact Page(REGEX Validation to prevent XSS and SQL Injection) | 1:30 -2:30:00 PM
2024-08-06 | Profile Page | 1:30 | Fixed AMAN's profile page to retrieve ORDER history and Updating Profile | 3-4:30 PM
2024-08-06 | Breadcrumbs Added | 0.5 | Breadcrumbs added to NAV menus | 5:30 PM 6:00 PM
2024-08-07 | Morning Group Meeting | 1 | Discussed Work Done So far, Set daily goals and assigned tasks to team | 9:00 - 10:00 AM | 9:00
2024-08-07 | UI Improvement in Product List Page | 0.5 | Made some UI improvements for better user experience | 10:15 - 10:45 AM
2024-08-07 | Billing and Checkout Page Logic Implementation | 3 | Created Controller, Updated ROutes and | 11:00 - 12:30, 1:30 - 3:00 PM
Fetched Stored Addresses
2024-08-07 | Last moment Brief Cart Summary Implemented | 1 | Fetched Shopping_cart page Summary to show products, | 3:00 - 4:00 PM
quantity, total and TAX split
2024-08-07 | REORDER button working in User Profile | 1 | User can see order history and can reorder same items | 4:00 - 5:00 PM
2024-08-07 | Application Flow setup (Routes Updation) | 1 | List View > Detail View> Wishlist / Add to Cart > | 7:00 - 8:00 PM
> shopping_cart> checkout > payment gateway
2024-08-08 | Morning Group Meeting | 1 | Reviews Worked So far, Set Daily Goal, Assigned Task to Team Members | 9:00 - 10:00 AM | 9:00
2024-08-08 | Coded HTML template for Product Review | 1 | HTML Template Created | 10:00 - 11:00 AM
2024-08-08 | Dynamic Review Page (Reviews Display, Style, | 2 | Dynamic Review Page (Controller) | 11:00 - 12:00, 1:00 - 2:00 PM
Ratings, Forms Created)
2024-08-08 | Review With Image Upload | 1 | Logic Created, Storage Link Creaed, Image Displayed with Review | 2:00 PM - 3:00 PM
2024-08-08 | Verified Purchase Review Logic Created | 2 | User Can Only Write Review for a Product, which has been ordered by him, | 5:00 - 7:00 PM
Implemented on Page
2024-08-08 | Login, Register, Verufy Email Page Styling | 1 | Modified Laravel Default Auth pages style | 7:00 - 8:00 PM
2024-08-09 | Morning Meeting | 1 | Review Work So Far, Assigned Daily Tasks | 9:00 - 10:00 AM | 9:00
2024-08-09 | Review Logic Revison | 0.5 | Review Form Enabled Only for Purchased Products, no access for un purchased | 10:20 - 10:50 AM
products
2024-08-09 | Wishlist Tweaks | 0.5 | Styling and logic revision | 11:00 - 11:30 AM
2024-08-09 | Thank you page with invoice | 3 | Created Dynamic Thank You page after Successful payment | 1:00 - 4:00 PM
Shows invoice to user
2024-08-09 | Mail Trap Integration | 1 | Contact Form queries, Fecthed and displayed in admin panel under | 6:00 - 7 PM
QUERIES section
2024-08-10 | User Profile (Final Version) | 5 | User Profile Management ( Order History) - List View of Orders, Detail View of | 7PM - 12 AM
Orders, Default Address Functionality (Checkout Form Picks up Default Address)
Address Update Functioanlity, Review List View in User profile
Showing User Pending Reviews Functionality and Access to Write Review
on Purchased Products
2024-08-12 | Morning Meeting | 1 | Discussed all the work done, assigned daily task | 9:00 - 9:35 AM, 10:00-10:30 AM | 9:00
2024-08-12 | Review CRUD Basic Set Up | 1 | AdminReviewControlller Methods Setup | 10:30-11:30 AM
2024-08-12 | Review CRUD Dynamic Setup | 2 | Review Crud Done | 1:00 -3:00 PM
Search By Category, Filter By Date, Rating, Review
Flagging
2024-08-12 | Queries CRUD Setup for (Contact Queries Directly | 2 | Table, Seeder, Controller Created, Fetched in Admin Panel | 3:00-4:00 AM, 7:00-8:00 PM
| in Admin Panel) |  | CRUD Creaated, Follow UP Notes Section created
2024-08-12 | Styking Tweaks | 1 | Product Pages Styling Tweaks to fololwing CARP Principle | 8:00-9:00 PM
2024-08-13 | Morning Group Meeting | 1 | Revised all the work, followed up pending tasks, assigned daily work | 9:00 - 10: 00 AM | 9:00
2024-08-13 | Styling Bug Fixing in Product List and Detail View Pages | 0.5 | Stylin issues fixed | 10:30-11:00 AM
2024-08-13 | Pages Responsiveness Test and Fixing | 1 | Run responsiveness tests and fixed issues | 11:00 - 12:00 PM
2024-08-13 | Help AMAN to Finalize USER CRUD | 1:30 | USER CRUD Issues Solved and FInished the Final Version | 1:00 - 2:30 PM
2024-08-13 | Queries CRUD issues Fixed | 0.5 | Some Data Storing Issues Fixed | 2:30 - 3:00 PM
2024-08-13 | Review CRUD - Review Flagging Logic | 2 | Flagged Table created, Made flagging reviews work, testing and bug fixing | 3:00 - 4:00, 7:00-8:00 PM
2024-08-13 | Review Form Validation - Request Created Implementes | 1 | Review Form Validation | 8:00 - 9:00 PM
2024-08-14 | Morning Group Meeting | 1 | Discussed all the operational work, checked website functioanlity | 9:00-10:00 AM | 9:00
Set Daily Goals
2024-08-14 | Front End Testing | 2 | Tested all the Pages and fucntionality, list out problems | 10:30 - 12:30PM
2024-08-14 | Bug Fixing | 3 | FIxed All the bugs which found in functionality | 1:30 - 4:30 PM
2024-08-15 | Online Meeting WIth Team | 1 | Discussed all the bugs pending and fixed, Set Daily Goals | 10:00 - 11:00 AM
2024-08-15 | Backend Testing | 3 | Checked all the functionality and list out backend bugs | 12:00 - 3:00 PM
2024-08-15 | Fixed Backend Bugs Found | 3 | Bug FIxingg, Final VErsion | 5:00 -8:00 PM
2024-08-15 | PPT for Presentation | 1 | Prepared PPT (MY PART) | 10:00 -11:00PM
2024-08-16 | Final Presentation | 10:00 -12:00 | Presented the Project With Team

## Yongdong
Date | Task | Time (Hours) | Remaks | Completion Time | Attendence
2024-07-30 | Brainstorming | 1 | Decided the Project Niche and Roles of Members | 10:30 | 9:00
2024-07-30 | Server set up | 2 | Apache2, PHP, MySQL, HTTPS | 13:00
2024-07-30 | GitHub repository set up | 1 | Create repository | 11:00
2024-07-31 | Morning Group meeting | 1 | Made Sure all team members' GIT Repo is working fine | 10:00 | 9:00
2024-07-31 | GitHub repository set up | 2 | Cloned original GitHub repository for reliable coordination | 12:00
2024-07-31 | GitHub public key | 1 | Helped team members to set up revised repo by adding PUB key | 14:00
2024-07-31 | Init project code | 1 | Init Laravel, Bootstrap | 15:00
2024-07-31 | Proposal | 2 | Server and Security | 20:00
2024-08-01 | Morning Group meeting | 0.5 | Database and Proposal Discussion | 9:30
2024-08-01 | Proposal Final | 2 | Merged Git commits and provided MANISH data from all team members | 11:30
2024-08-01 | Refactor database migration | 2 | Add soft delete, make field names more standard, delete unnecessary tables | 14:30
2024-08-01 | Refactor database seeders | 2 | Change seeders to match migration | 16:30
2024-08-02 | Morning Group meeting | 0.5 | Deal with conflicts locally, merge, and pull request | 9:00
2024-08-02 | Route | 3 | Create all well routes | 12:00
2024-08-02 | Blade and Controller | 3 | Create all well controller and blank blade files to connect together | 15:00
2024-08-04 | Database | 2 | Order tables add recipient info, migration, and seeder | 11:00
2024-08-04 | Controller | 1 | Payment tables add card, payer name, migration, and seeder | 12:30
2024-08-04 | Controller | 2 | ProductController | 14:00
2024-08-05 | Controller | 2 | WishlistController | 10:00
2024-08-05 | Controller | 2 | CartItemController | 12:00
2024-08-06 | Admin route and blade | 1 | Init admin routes and blade files | 9:30
2024-08-06 | Config tables | 2 | Config migration, seeder, model for Home Page banner config | 11:30
2024-08-06 | Fix bug | 2 | Fix Laravel Vite SCSS load bugs, login bugs | 14:00
2024-08-07 | Morning Group Meeting | 1 | Discussed Work Done So Far, helps members to fix bug | 9:00
2024-08-07 | Product Detail Page | 1 | Add or remove product to wishlist | 10:00
2024-08-07 | WishlistController | 0.5 | Render wishlist page blade | 11:00
2024-08-07 | WishlistController | 1 | Add product into cart and remove from wishlist | 12:00
2024-08-07 | WishlistController | 0.5 | Remove product from wishlist | 13:00
2024-08-07 | Front-end structure | 1.5 | Concise header component and fix home page bugs | 14:00
2024-08-07 | Front-end structure | 2 | Remove most CDN JS, CSS and use Vite to manage all SCSS and JS | 16:00
2024-08-07 | 5bx | 1 | 5bx init; 5bx .env and 5bx config.php setting. Create 5bx Service | 17:00
2024-08-07 | CheckoutController | 2 | CheckoutRequest validation and query user's cart to create an order | 19:00
2024-08-07 | Git | 1 | Review and merge pull request | 20:00
2024-08-08 | Git | 1 | Review and merge pull request | 9:00
2024-08-08 | UI | 1 | Unify all pages' UI | 10:00
2024-08-08 | Cart | 2 | Create order when go to check and check product stock | 11:00
2024-08-08 | Payment Page | 2 | Dynamic tax and shipping fee calculation. Country and province API | 13:00
2024-08-08 | Process checkout | 1 | Validate shipping address, billing address, and payment info request | 15:00
2024-08-08 | Process checkout | 1 | Calculate tax, shipping fee, total amount | 16:00
2024-08-08 | Process checkout | 1 | Using 5bx to verify credit card info | 17:00
2024-08-08 | Process checkout | 1 | Update order tax, amount info. Create payment and transaction | 18:00
2024-08-08 | Meeting | 1 | Help members fix bugs | 19:00
2024-08-09 | Git | 1 | Review and merge pull request | 9:00
2024-08-09 | Admin init | 2 | Route, blank controller,blank blade, tailwind, daisyui
2024-08-09 | Admin Layout | 4 | Header, footer, sidebar, pagination, flash and layout
2024-08-09 | Admin Order | 2 | Order List, Order details
2024-08-09 | Admin List | 2 | Reviews, payments list page ui
2024-08-10 | Checkout | 4 | Refactor checkout page and processor
2024-08-12 | Git | 1 | Review and merge pull request
2024-08-12 | AWS Serve | 2 | Deploy Project
2024-08-12 | Admin Order List | 1 | Update status
2024-08-12 | Route | 1 | Separate web.php into different files
2024-08-12 | Checout | 1 | Fix bugs
2024-08-12 | Admin Ui | 2 | Tweak admin ui
2024-08-12 | Meeting | 1 | Help members fix bugs
2024-08-13 | Git | 1 | Review and merge pull request
2024-08-13 | Meeting | 1 | Help members fix bugs
2024-08-13 | Storage | 2 | Move images to storage, create link to fix the upload images bugs
2024-08-13 | Admin dashboard | 1 | Order and revenue statics
2024-08-13 | Admin dashboard | 1 | Fix home ui conflicts
2024-08-13 | Admin Sidberbar | 1 | Active menu style
2024-08-14 | Admin | 2 | Tweak User Management UI
2024-08-14 | Admin | 2 | Tweak Query Management UI
2024-08-14 | Login and Register | 1 | Tweak UI
2024-08-15 | Storage | 2 | Fix storage and upload file bugs
2024-08-15 | Favicon | 0.5 | Set Favicon
2024-08-15 | Checkout | 2 | Fix expiry date bug
2024-08-15 | doc | 0.5 | User emails, mysqldump,copyright
2024-08-15 | Fix bugs | 1 | Fix reviews bugs in live version

## Shivangi
Date | Task | Time (Hours) | Remaks | Completion Time | Attendence
2024-07-30 | Brainstorming | 1 | Decided the Project Niche and Roles of Memebers | 11:30 | 9:00
2024-07-30 | Database Modelling/Design (Physical) | 2.5 | Pre-Planned the blueprint of database and completed physical design of the database schema (tentative). Included table definitions, relationships, and constraints.
2024-07-31 | Group Meeting | 1 | Discussed the Mock Database Model Created on 30th July | 10:00 | 9:00
2024-07-31 | Database ERD Done | 1.5 | Actual Databse ERD created | 12:30
2024-07-31 | ERD with Additional Tables | 1 | Added Values ERD created | 13:30
2024-07-31 | Frontend Sitemap Started | 1 | Front end site map completed | 15:00
1st Aug | Group Meeting | 0.5 | Reviewed Database and Proposal | 9:30 | 9:00
1st Aug | Proposal | 1 | Added Database and Sitemap to Proposal | 10:30
1st Aug | Solved issues | 0.5 | Solved conflict issues and composer installation issue,updated the database [] | 11:00
1st Aug | Seeded Data into database, created tables, migration | 3 | Database Seeding with Aman and Yongdong | 14:30
2nd Aug | Morning Group Meeting | 0.5 | discussion for database and proposal | 9:00 | 9:00
2nd Aug | update database files | 1 | some changes were required in the database, so updated it, with Yongdong | 10:00
2nd Aug | Solve issue of server | 1 | local server not working solve issue for that | 11:00
2nd Aug | Start working on front end pages | 1 | Discussion about front-end structure and create a new page product details | 11:30
2nd Aug | Done with product detail page | 3 | make new page about us with html, css | 3:00
2nd Aug | Include header and footer files | 1 | Added header and footer in exisiting pages, and solve some issue of css | 3:30
6th Aug | Morning Group Meeting | 0.5 | Discusses previous work and Assigned Tasks for Making Dynamic Pages | 9.00 AM | 9:00
6th Aug | Authentication -Linked register, login and logout | 2 | make website authenticate, that is user able to register and login page | 11:00
6th Aug | header and footer navigation | 0.5 | added navigation to all pages for header and footer | 12:00
6th Aug | Fixed CSS issue | 1 | make diff file for css and load into blade page for fixing css issue | 2:00
6th Aug | product details page update | 2 | fetch all data from database for product details page | 4:00
6th Aug | make shopping cart page | 3 | create blade template, controller and css for shopping cart | 6:00
7th Aug | Morning Group Meeting | 0.5 | Discussed Work Done So far, Set daily goals and assigned tasks to team | 9:00
7th Aug | Shopping Cart Page | 2 | Create new shopping cart page, make css and upgrade data from database | 11:00
7th Aug | Product detail Page | 1 | make it full dynamic and make add to cart button icon working | 1:00
7th Aug | Payment summary | 2 | in shopping cart, have added payment summary session - and upgrade in javascript | 3:00
7th Aug | Update Database -Products | 1 | added new filed for long description, seeded data and also load it dynamic | 4:30
7th Aug | Make javascripts | 2 | make javascript for counting product price and taxes etc (total, subtotal, PST,.. ) | 5:30
7th Auh | UI improvement | 1 | update UI for product details and shopping cart page | 7:00
8th Aug | Morning Group Meeting | 0.5 | Reviews Worked So far, Set Daily Goal, Assigned Task to Team Members | 9:00 | 9:00
8th Aug | Remove uncessary stuff from cart page | 1 | Review the cart page elements that are not needed. | 10:00
8th Aug | crate notification icon for cart and logic | 1.5 | Add a cart icon with a notification badge in the header section and did logic | 11:00
8th Aug | Try to solve issue of add to cart button | 3 | Determine why the "Add to Cart" button is not working, update all payment details with backend | 3:40
8th Aug | Update stock value in the database | 1 | Retrieve the current stock value from the database and update it | 5:00
8th Aug | seeding more data product descriptions | 1 | Create a database seeder to add more product descriptions. | 6:00
8th Aug | change short desc for product detail page | 1 | Locate the short description field in the product detail page template (product_details.blade.php). | 7:30
9th Auh | Morning Group Meeting | 0.5 | Reviews Worked So far, Set Daily Goal, Assigned Task to Team Members | 9:00 | 9:00
9th Auh | Fixed Add to cart issue | 2 | Change javascript for page | 11:30
9th Auh | Update CSS | 1 | update css of shopping cart | 1
9th Auh | Admin panel Started | 0.5 | make controller and updated database data for starting admin panel work | 2:00
9th Auh | Product - Index | 1 | Make Product admin page to show all listing of products | 3:00
9th Auh | Product - Create | 1 | make create product page of admin | 4:00
11th Auh | Product - Edit | 2 | make product edit page | 11:00
11th Auh | Product - delete | 1 | added delete functionality in product | 1:00
11th Auh | update css | 1 | Modified some code for products page and update some css | 2:00
2024-08-12 | Group Meeting | 0.5 | Discussed work completed so far and planned daily work | 9:30 | 9:00
2024-08-12 | Seeder | 0.5 | seeded product data upto 50 products | 10:00
2024-08-12 | Fixed review button issue | 0.5 | product details page- review button issue - added again | 11:00
2024-08-12 | Admin dashboard Logs | 2.5 | added users and admin tracking logs | 2:30
2024-08-12 | Filter logs | 1 | filter logs by admin and user, and also only allow login and logout logs | 3:30
2024-08-13 | Git | 1 | solve conflict issues
2024-08-13 | Meeting | 1 | Discuss all task for today
2024-08-13 | Logs | 2 | Solve issue of logs, make new log files and generate new logs and show it
2024-08-13 | CSS | 1 | Update some css of product details page
2024-08-13 | Bug fixing | 1 | Find bugs on pages and try to solve it, like css, button working
2024-08-13 | testing | 1 | test website and finding bugs
2024-08-14 | Group Meeting | 0.5 | Discussed work done so far, discussed errors and planned daily work | 9:30 | 9:00
2024-08-14 | Admin Logs | 2 | updated user logs file on admin, and filter it | 12:30
2024-08-14 | Changes on web pages | 2 | modified product details bottom link pages, added delete button verification, change quanity verification from backend as well et | 23:00 PM
2024-08-15 | Group Meeting | 0.5 | Zoom meeting related to presenting our work
2024-08-15 | Fixed issue for product images on server | 1 | solve issue related long desc, and image for product admin panel

## Aman
Date | Task | Time (Hours) | Remaks | Completion Time | Attendence
2024-07-30 | Brainstorming | 1 | Decided the Project Niche and Roles of Members | 11:30 | 9:00
2024-07-30 | Database Modelling/Design (Physical) | 2.5 | Completed physical design of the database schema(tentative). Included table definitions, relationships, and constraints.
2024-07-31 | Group-meeting | 1 | Git Repo Setup, ERD discussion | 10:00 | 9:00
2024-07-31 | ERD with Shivangi | 1.5 | ERD created | 12:30
2024-07-31 | ERD with ADDED values | 1 | ERD created with added Vaules | 13:30
2024-07-31 | Admin Dashboard Sitemap | 3 | CRUD Sitemap Created | 17:30
2024-08-01 | Morning Group Meeting | 0.5 | Work Review , Proposal Review and Database Discussion | 9:30 | 9:00
2024-08-01 | Proposal | 1 | Added Backend Sitemap and Database Part to Proposal | 10:30
2024-08-01 | Database seeding and migrations | 3 | Database seeding along with Shivangi and YongDong | 14:30
2024-08-01 | started working on the front-end (about page) | 2.5 | Worked on about page (css needs to be fixed) | 18:15
2024-08-02 | Morning Group Meeting | 0.5 | discussion about the page appearance and css fixing | 9:30 | 9:00
2024-08-02 | completed the about page | 2.5 | about page completed | 11::30 PM
2024-08-02 | fixed about styling and design conflicts | 2 | design/styling fixed | 13:30
2024-08-02 | made about.scss temporarily to mitigate the conflicts | 0.5 | setup about.scss for temporarily purposes/backup css | 14:45
2024-08-06 | Morning Group Meeting | 0.5 | Discussion about making profile page | 9:30 | 9:00
2024-08-06 | Profile page Dynamic conversion | 2 | Converted profile page from HTML to profile.blade.php | 11:30
2024-08-06 | Profile page styling fix | 0.5 | converted styling and made profile.scss for separation purposes | 12:00
2024-08-06 | profile page dynamically collecting data | 2.5 | fetching data, collecting history of order for current logged in user | 14:30
2024-08-06 | logout functionality | 0.75 | logout functionality worked successfully (notifications/flash pending) | 15:15
2024-08-06 | social icons and contact icons | 0:5 | removed cdn and added custom icons | 0:45
2024-08-06 | fixing the contact box | 1 | fixed the contact box in the center position and fixed css, icons etc | 1:30
2024-08-07 | Morning Group Meeting | 0.5 | Reviewed work done so far, and about creating faq page and policy page | 9:30 | 9:00
2024-08-07 | Created FAQ HTML template | 2.5 | HTML template for FAQ page created | 12:00
2024-08-07 | Design/Styling for FAQ page | 0.5 | Design/Styling fixed for FAQ page | 13:30
2024-08-07 | Converted template to FAQ blade | 1 | FAQ blade converted and finalized, linked to footer under (Support) | 14:30
2024-08-07 | Created Privacy Policy HTML template | 2.5 | HTML template for Privacy Policy page created | 17:00
2024-08-07 | Design/Styling for Privacy Policy Page | 0.5 | Design/Styling fixed for Privacy Policy Page | 17:30
2024-08-07 | Converted template to Privacy Policy blade | 1 | Privacy Policy blade completed | 20:30
2024-08-08 | Morning Group Meeting | 0.5 | related to changing the structure of our pages and making visually appealing | 9:30
2024-08-08 | Structure of FAQ (toggle added) | 0.5 | Changed structure, Toggle was not working before update, now working | 10:00
2024-08-08 | Structure of Privacy Policy | 1.5 | Changed the structure of privacy policy page, linked to footer | 11:30
2024-08-08 | Cancellation-Refunds HTML template | 2.5 | HTML template for Cancellation-Refunds Created | 14:30
2024-08-08 | Design/Styling for Cancellation-Refunds page | 0.5 | Design/Styling completed for for Cancellation-Refunds page | 15:00
2024-08-08 | Cancellation-Refunds blade | 1.5 | Cancellation-Refunds blade converted and finalized, linked to footer under (Support) | 16:30
2024-08-09 | Morning Group Meeting | 0.5 | Reviewing the work done so far | 9:30 | 9:00
2024-08-09 | Styling for all pages done so far | 1 | Finalized the styles for cancellation-refunds blade, FAQ | 10:30
2024-08-09 | Admin/user Management AdminUserController | 1 | started working on index method in AdminUserController | 11:30
2024-08-09 | Admin/user Management AdminUserController | 0.5 | created all other methods like create | 12:00
2024-08-09 | Admin/user Management AdminUserController | 2 | created methods like store, edit, update, destroy | 15:00
2024-08-09 | user model | 0.5 | additional fillables to the user model as a requirement for admin/user management | 15:30
2024-08-11 | user index blade | 2 | made a list(index) of users, admin or customers | 13:30
2024-08-11 | user create blade | 0.75 | made a create blade for listing users (users management) | 14:15
2024-08-11 | user edit blade | 0.75 | made an edit blade for users (users management) | 15:00
2024-08-12 | Morning group meeting | 0.5 | change in structure of fetching data (payments and orders) table for users management | 9:30
2024-08-12 | User Controller | 2.5 | modifications in all methods | 12:00
2024-08-12 | user index blade | 1.5 | collected addresses for user from payments and orders table | 14:30
2024-08-12 | Create blade | 0.75 | yet to fix this, getting error | 15:15
2024-08-12 | show blade | 0.75 | working now but still needs modifications | 16:00
2024-08-13 | Morning Group Meeting | 0.5 | related to completing CRUD today and start making a bug testing report from tomorrow | N/A | 10:55
2024-08-13 | USER CRUD modifications | 1 | fetching data from default address instead of orders and payments tables | 23:55
2024-08-13 | Controller methods | 1 | controller methods changed fetching data from default_address done | 13:00
2024-08-13 | index blade refix | 0:5 | index blade refixed as per controller | 13:30
2024-08-13 | create blade | 0:5 | create blade refixed as per controller | 14:00
2024-08-13 | show blade | 0:5 | show blade refixed as per controller | 14:30
2024-08-13 | edit blade | 0.5 | edit blade refixed as per controller | 15:00
2024-08-14 | Morning Group Meeting | 0.5 | Related to Bugs fixings as per assigned tasks | 9:30 | 9:00
2024-08-14 | Bug testing AdminUserController | 1 | AdminUserController is protected against various attacks, only accepts related inputs | 10:30
2024-08-14 | bug report and testing | 1.5 | bug report and testing by me and Shivangi | 12:00
2024-08-15 | Group Meeting | 0.5 | Zoom meeting related to presentation on 16th August | 15:30
2024-08-15 | Live version full testing | 3 | Full testing of the final site and finding out the bugs if any and assigning it to team members | 11 AM to 2 PM
2024-08-16 | Presentation | 0.25 | Final Presentation | 11:35

## Dongqing
Date | Task | Time (Hours) | Remaks | Completion Time | Attendence
2024-07-30 | Brainstorming | 1 | Decided the Project Niche and Roles of Memebers | 11:30 | 9:00
2024-07-30 | Design | 7 | Landing page, list view page design
2024-07-31 | Group-meeting | 1 | Presented and explained all the work we've done so far, and planned the to-do list for today | 10:00 | 9:00
2024-07-31 | Design Modification | 0.5 | Modified landing page and list view | 13:30
2024-07-31 | Design | 6 | Detail page and About us page design | 20:30
2024-07-31 | Design Section of Proposal | 1 | Wrote design solution of the proposal | 23:59
2024-08-01 | Morning Group Meeting | 0.5 | Reviews Work and Design | 9:30 | 9:00
2024-08-01 | Added Mine Work of Work in Proposal | 1 | Psoposal Part of Design | 10:30
2024-08-01 | Made revisions in Design | 1.5 | Made changes as steve advised | 12:00
2024-08-01 | Front End folder structure | 0.25 | Created front end folder structure | 1.30PM
2024-08-01 | Homepage html | 2.5 | Created homepage html file | 17:00
2024-08-01 | Homepage CSS | 4 | Keep working on CSS style | 23:59
2024-08-02 | Homepage CSS | 1 | Multiple issues fixed | 1:30
2024-08-02 | Morning Group Meeting | 0.5 | Reviews Front end work | 9:30 | 9:00
2024-08-02 | CSS modification | 2.5 | Solved responsive problem, modified header and footer | 12:00
2024-08-02 | Other front end pages | 1.5 | Created blade files, created wishlist page | 15:30
2024-08-06 | Group-meeting | 1 | Reviewed work and planned for backend | 10:00 | 9:00
2024-08-06 | Product image | 0.5 | product images collected | 11:00
2024-08-06 | Migration, Seeder, Controller | 2.5 | Modified migrations, seeders and controller | 14:30
2024-08-06 | Dynamic home.blade.php | 3 | changed static homepage into dynamic page | 19:30
2024-08-06 | Presenting problem fixed | 1 | fixed homepage presenting problems | 20:30
2024-08-07 | Group Meeting | 1 | Reviewed work done so far and set to do list | 10:00 | 9:00
2024-08-07 | flash message | 2 | Modified login and register controllers, created flash blade and set flash message for register, login and logout | 0:00
2024-08-07 | Search form input validation | 0.5 | Product controller modified, for validating user input in search query | 13:30 AM
2024-08-07 | User controller modified | 1 | Validated and sanitized user input; display error message under each input field | 14:30 AM
2024-08-07 | profile blade modified; user profile Input validation | 1 | Validated and sanitized user input for profile page; display error message under each input field | 15:30 AM
2024-08-08 | Group Meeting | 0.5 | Discussed work done so far and daily work | 9:30 | 9:00
2024-08-08 | Controller & Route for dashboard | 0.25 | Created home controller, set route | 10:00
2024-08-08 | Dashboard blade template | 2 | Created dashboard template, including header, footer, sidebar, data section and log table. HTML data implemented | 13:30 PM
2024-08-08 | Dashboard layout design | 2 | Designed dashboard layout | 15:30 PM
2024-08-08 | Css presenting issue | 0.5 | Modified css style | 16:00 PM
2024-08-08 | CRUD set up for category | 1 | Created functions, created index blade | 21:00 PM
2024-08-09 | Group Meeting | 0.5 | Discussed work done so far and daily work | 9:30 | 9:00
2024-08-09 | Fixed admin route problem; CSS modified | 0.5 | Fixed admin route problem with Yongdong; modified css | 10:00
2024-08-09 | AdminCategoryController | 2 | Category controller function completed, including index, create, store, edit, update and destroy | 0:30
2024-08-09 | Category index blade | 1.5 | Continuing working on category index blade | 14:30 PM
2024-08-09 | Category create blade | 0.5 | Created category create blade | 15:00 PM
2024-08-09 | Category edit blade | 0.5 | Created category edit blade | 23:00 PM
2024-08-11 | Backend css modified | 0.5 | Modified backend css style
2024-08-11 | Admin dashboard mock up | 2 | Created admin dashboard mock up
2024-08-12 | Group Meeting | 0.5 | Discussed work completed so far and planned daily work | 9:30 | 9:00
2024-08-12 | Backend Css | 0.5 | Modified Backend css
2024-08-12 | Admin dashboard design mockup | 1.5 | Finished admin dashboard design | 14:30 PM
2024-08-12 | Seeder | 0.5 | Modified product seeder | 15:30 PM
2024-08-12 | Admin dashboard | 1.5 | Add Top Seller table into admin dashboard and style this section | 23:00 PM
2024-08-13 | Group Meeting | 1 | Discussed work done so far, discussed errors and planned daily work | 10:00 | 9:00
2024-08-13 | Fix bugs | 1.5 | Fixed bugs for category CRUD, including create, edit and image path | 0:00
2024-08-13 | Login, register and reset password | 2 | Created unitized forms and layout for login, register and reset password page | 23:00 PM
2024-08-14 | Group Meeting | 0.5 | Discussed work done so far, discussed errors and planned daily work | 9:30 | 9:00
2024-08-14 | Login, register, password reset | 3 | Recreated login, register and password pages; style each of them | 12:30
2024-08-14 | Css modification for all pages | 6 | Modified product list page, product detail page, shopping cart page, checkout page, contact us page, about us page | 23:00 PM
2024-08-15 | Wishlist | 0.75 | Wishlist css style modified | 14:30PM
2024-08-15 | Group Meeting | 0.5 | Zoom meeting to prepare for presentation | 15:30 PM
2024-08-15 | Product Review | 1 | Product review css style modified | 19:30 PM